## Lembar1
WBS | Task | Duration | Predecessors | Successors | Budget | %C Claim 01 | %C Claim 02 | %C Claim 03 | %C Claim 04 | %C Claim 05 | %C Claim 06
1 | CONTRACT AWARD |  |  | 5,8,73,75,113
2 | PRACTICAL COMPLETION |  | 10,108,115,145,6,70,105,75
5 | Schedule A - Roadworks Dysart Bypass Road Widening Preliminaries - Site establishment, Provision for Workplace Health & Safety, Site Cleanup and Dis-establishment | 2 | 3,8 | 6,7,9,45,74,73,76,11,15,16,71,79,80,119,120 | 34725 | 80% | 80% | 80% | 80% | 85% | 85%
6 | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 71 | 5 | 4 | 76266.8311 | 10% | 60% | 70% | 80% | 85% | 85%
7 | Construction Setout by Contractor | 9 | 5 | 9 | 23680 | 100% | 100% | 100% | 100% | 100% | 100%
8 | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | 1 | 3 | 5 | 10400 | 100% | 100% | 100% | 100% | 100% | 100%
9 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 2 | 5,7 | 18 | 6800 | 100% | 100% | 100% | 100% | 100% | 100%
10 | As Constructed Survey Data to Council Requirements. | 6 | 44 | 4 | 8880 | 0% | 0% | 0% | 0% | 0% | 0%
11 | Geotechnical Testing by NATA Registered laboratory - Subgrade CBR tests (soaked 4 day, 4 point) (allow 3 confirmation tests on final subgrade for pavement design) | 1 | 5 | 12 | 2700 | 0% | 100% | 100% | 100% | 100% | 100%
12 | Subgrade Compaction testing as specified | 1 | 11 |  | 5926.6667 | 0% | 28.57% | 57.14% | 89.29% | 89.29% | 89.29%
13 | Sub-Base Compaction testing as specified - assume 1 layer | 2 | 25 | 24 | 5926.6667 | 0% | 28.57% | 57.14% | 89.29% | 89.29% | 89.29%
14 | Base Compaction testing as specified | 1 | 23 | 27 | 5926.6667 | 0% | 28.57% | 57.14% | 89.29% | 89.29% | 89.29%
15 | Sub-Base Quality Testing as specified; Full Atterbergs and grading plus full Quarry Stockpile results - assume 1 layer | 2 | 5 | 26 | 2580 | 0% | 100% | 100% | 100% | 100% | 100%
16 | Base Quality Testing as specified; Full Atterbergs and grading plus full Quarry Stockpile results. | 4 | 5 | 24 | 2580 | 0% | 100% | 100% | 100% | 100% | 100%
17 | Culvert Trench Backfilling - Compaction Tests as ordered | 1 |  |  | 2328.3333 | 0% | 100% | 100% | 100% | 100% | 100%
18 | Clearing & Grubbing and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 3 | 145,9 | 19,45,152 | 12317.3333 | 0% | 100% | 100% | 100% | 100% | 100%
19 | Earthworks - excavate and place as embankment as directed - Cut to fill - Ch 18 to Ch 2801 to achieve boxed out widening of existing road x 350mm deep - refer type cross section (total of 2804 m3 of Cut and 225 m3 of Fill) balance of cut material will b | 7 | 18152 | 20151 | 33689.752
20 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 1 | 19151 | 21 | 2514.8
21 | Provisional Item Allowance to excavate an additional 150mm depth to the pavement box if required over 25% of length (material to spoil at IRC Tip) - Only if ordered by the Superintendent | 2 | 20 | 22 | 9338.148
22 | Prepare Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) Bypass Road Widening from Ch 18 to Ch 2801 | 7 | 21 | 45 | 32988.3385
23 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Bypass Road Widening Ch 18 to 2801 | 3 | 24153 | 14 | 15618.0152 | 0% | 0% | 100% | 100% | 100% | 100%
24 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - QT Type 2.1 @ 150mm deep x widening area | 5 | 25,16,13 | 23153 | 131510.4074
25 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 -Upper Sub-Base QT Type 2.3 @ 200mm deep x widening area | 8 | 26 | 24,13 | 211113.9796
26 | Gravel Pavement Base In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Bypass Road Widening Ch 18 to Ch 2801 - Provisional Item Allowance for Lower Sub-Base QT Type 2.5 @ 150mm deep x widening area over selected 25% of l | 3 | 67,15 | 25 | 48873.2138
27 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road LHS Shoulder 1 metre wide Ch 510 to Ch 650 | 1 | 14 | 28 | 754.6 | 0% | 0% | 100% | 100% | 100% | 100%
28 | Primerseal complete in place (10mm stone ); spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED Bypass Road Widening plus 1 metre wide shoulder RHS Ch 510 to Ch 650 | 1 | 27 | 29 | 1999.69 | 0% | 0% | 100% | 100% | 100% | 100%
29 | Bypass Road 7 metre section over where New RCBC culvert placement approx Ch 600 | 1 | 28 | 30 | 199.43 | 0% | 0% | 100% | 100% | 100% | 100%
30 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED Bypass Road Widening Ch 18 to Ch 510 | 1 | 29 | 31 | 5198.424 | 0% | 0% | 100% | 100% | 100% | 100%
31 | Bitumen Seal - First Coat complete in place (16mm primerseal ) ; spray rates nominally to be 1.6 l/sqm C170 - SHOULDER WIDENING, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 1 | 30 | 32 | 22720.698 | 0% | 0% | 100% | 100% | 100% | 100%
32 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED -Bypass Road Widening Ch 18 to Ch 510 | 1 | 31 | 33 | 13676.124 | 0% | 0% | 100% | 100% | 100% | 100%
33 | Bitumen Seal - Second Coat complete in place (10mm second coat); spray rates nominally to be 1.2 l/sqm C170 - 7 METRE WIDE SEAL, SEAL DESIGN TO BE CONFIRMED - Bypass Road Widening Ch 650 to Ch 2801 | 2 | 32 | 34,35FF | 59791.347 | 0% | 0% | 49.84% | 49.84% | 86.19% | 86.19%
34 | DG10 Asphaltic Concrete Pavement 35mm minimum thickness - complete in place including sawcut edges and neat smooth joins - Bypass Road Floodway - Ch 510 to Ch 650 (x 9 metres wide) | 1 | 33,37 | 38,41 | 34546.8375 | 0% | 0% | 0% | 0% | 100% | 100%
35 | Access Ch 826 RHS (Dysart Horse Performance Association) - Provide smooth transition between existing access and new shoulder (no pipe required; reinstate to similar) | 1 | 33FF | 36FF | 723.8 | 0% | 0% | 0% | 100% | 100% | 100%
36 | Access Ch 1642 RHS (Cemetery Carpark Access) - Reinstate sealed driveway between New shoulder and Carpark Access (no works on culvert required); neat smooth join. | 1 | 35FF | 37FF | 1014.8 | 0% | 0% | 0% | 0% | 0% | 0%
37 | Access Ch 1660 RHS (Cemetery Access) - Reinstate sealed driveway between New shoulder and Cemetery Access (no works on culvert required); neat smooth join. | 1 | 36FF | 34 | 1014.8 | 0% | 0% | 0% | 0% | 0% | 0%
38 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 8 | 34 | 39 | 21352.5675 | 0% | 0% | 0% | 0% | 100% | 100%
39 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters & drains) | 4 | 38 | 40 | 27731.05 | 0% | 0% | 0% | 0% | 0% | 0%
40 | Soil Management Measures inclusive of: Rock check dams as directed | 2 | 39 |  | 10842.6667 | 0% | 0% | 0% | 0% | 0% | 0%
41 | Supply and Install New Guide Posts - allow new on widened side only and adjacent to end wall extensions | 2 | 34 | 42 | 2000 | 0% | 0% | 0% | 100% | 100% | 100%
42 | Supply and Install Floodway Depth markers (G9-22-1A) | 1 | 41 | 43 | 957.6 | 0% | 0% | 0% | 100% | 100% | 100%
43 | Remove Signs for widening and reinstate | 1 | 42 | 44 | 338.8 | 0% | 0% | 0% | 100% | 100% | 100%
44 | Provisional Item Guardrail as per Note 5 on plan 842-R02 allow (3 lengths of Armoc ® 'W' Beam type XR & standard posts rammed into the ground with bull nose terminal ends) Only if ordered by Superintendent | 4 | 43 | 10 | 28000 | 0% | 0% | 0% | 0% | 0% | 0%
45 | Schedule B - Drainage Dysart Bypass Rd: Ch 49.400 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 dia SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay and backfi | 1 | 5,18,22 | 46 | 1297.351 | 100% | 100% | 100% | 100% | 100% | 100%
46 | 1 x 375 dia Endwall , Precast Type with wings Complete in place, incl. Excavate, sand, supply and install. | 1 | 45 | 47 | 1257.8 | 0% | 100% | 100% | 100% | 100% | 100%
47 | Ch 300 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 46 | 48 | 1344.931 | 100% | 100% | 100% | 100% | 100% | 100%
48 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | 47 | 49 | 2338.85 | 0% | 100% | 100% | 100% | 100% | 100%
49 | Ch 600 Extend 2/1800 x 600 RCBC and Add 3 New Cells 1800 x 600, Installation to Main Roads Std Dwg 1359 - Extend existing 2/1800 x 600 RCBC Complete in place, incl. removal of existing Endwalls with care, excavate, sand, supply, lay & backfill. | 4 | 48 | 50 | 20898.8887 | 0% | 100% | 100% | 100% | 100% | 100%
50 | Install NEW 3/1800 x 600 RCBC adjacent to existing lengthened Culvert Complete in place, incl. excavate, sand, supply, lay and backfill. | 2 | 49 | 51 | 64286.6382 | 0% | 100% | 100% | 100% | 100% | 100%
51 | NEW 5/1800 x 600 Cast Insitu Endwalls and Aprons to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct (existing to be removed) | 1 | 50 | 52,54 | 2161.4 | 0% | 100% | 100% | 100% | 100% | 100%
52 | Excavate inlet and outlet at 0.5% grade with 10m base width to connect to existing drains neatly and smoothly. | 1 | 51 | 53 | 1661.4 | 0% | 100% | 100% | 100% | 100% | 100%
53 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock. | 1 | 52 | 68 | 3372.6 | 0% | 0% | 100% | 100% | 100% | 100%
54 | Ch 800 Extend 4/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 51 | 55 | 2118.874 | 100% | 100% | 100% | 100% | 100% | 100%
55 | 4 x 450 Cast Insitu Endwall ,Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | 54 | 56 | 2338.85 | 0% | 100% | 100% | 100% | 100% | 100%
56 | Ch 1300 Extend 4/450 dia SRC Pipe Class 2 SRC, Installation to Main Roads STD DWG 1359 - 4 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing headwall with care, excavate, sand, supply, lay & backfill. | 1 | 55 | 57 | 2078.392 | 100% | 100% | 100% | 100% | 100% | 100%
57 | 4 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | 56 | 58 | 2338.85 | 0% | 0% | 100% | 100% | 100% | 100%
58 | Ch 1500 Extend 375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 57 | 59 | 1306.8446 | 100% | 100% | 100% | 100% | 100% | 100%
59 | 1 x 375 Endwall with wings , Precast Type Complete in place, incl. Excavate, sand, supply and install. | 1 | 58 | 60 | 1257.8 | 0% | 100% | 100% | 100% | 100% | 100%
60 | Ch 1749.800 Extend 2/450 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 450 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 59 | 61 | 2147.6137 | 100% | 100% | 100% | 100% | 100% | 100%
61 | 2 x 450 Cast Insitu Endwall to Main Roads Std Dwg 1306 Complete in place, incl. Excavate, supply and construct | 1 | 60 | 62 | 2147.975 | 0% | 100% | 100% | 100% | 100% | 100%
62 | Ch 1949.800 Extend 2/750 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 750 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 61 | 63 | 3398.3134 | 100% | 100% | 100% | 100% | 100% | 100%
63 | 2 x 750 Cast Insitu Endwall ,Main Roads Std Dwg 1304 Complete in place, incl. Excavate, supply and construct | 1 | 62 | 64 | 4019.9 | 0% | 0% | 100% | 100% | 100% | 100%
64 | Ch 2200 Extend 1/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 1 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 1 | 63 | 65 | 1332.7946 | 100% | 100% | 100% | 100% | 100% | 100%
65 | 1 x 375 Endwall , Precast Type with wings, Complete in place, incl. Excavate, sand, supply and install. | 1 | 64 | 66 | 892.8 | 0% | 100% | 100% | 100% | 100% | 100%
66 | Ch 2720 Extend 2/375 dia SRC Pipe Class 2, Installation to Main Roads Std Dwg 1359 - 2 x 375 SRC Pipe Cl 2 Complete in place, incl. removal of existing Endwall with care, excavate, sand, supply, lay & backfill. | 2 | 65 | 67 | 1980.785 | 100% | 100% | 100% | 100% | 100% | 100%
67 | 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs 1304 and 1371 Complete in place, incl. Excavate, supply and construct | 1 | 66 | 68,26 | 947.8 | 0% | 100% | 100% | 100% | 100% | 100%
68 | Excavate inlet and outlet at 0.5% grade with 1.0m base width to connect to existing drains neatly and smoothly. | 1 | 67,53 | 69 | 1658.0838 | 0% | 100% | 100% | 100% | 100% | 100%
69 | Rip Rap Rock Protection in 250mm dia rock (layer 0.5m thick) to Outlet to extend 10m past culvert end and up batters a minimum of 1m - leave neat, tidy and even surface to rock | 1 | 68 | 70 | 2322.6 | 0% | 0% | 0% | 0% | 0% | 0%
70 | Ch 2800 Take up and stack existing 1/600 x 300 RCBC and backfill to reinstate roadway. | 1 | 69 | 4 | 4666.85 | 0% | 0% | 0% | 0% | 0% | 0%
71 | Schedule C - Dysart Middlemount / Dysart Bypass Intersection - Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 13 | 5 | 72 | 28325.0469 | 0% | 80% | 80% | 80% | 100% | 100%
72 | Construction Setout by Contractor | 4 | 71,73 | 74 | 5180 | 0% | 100% | 100% | 100% | 100% | 100%
73 | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | 1 | 3,5 | 72 | 2800 | 0% | 100% | 100% | 100% | 100% | 100%
74 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | 5,72 | 81 | 3200 | 0% | 100% | 100% | 100% | 100% | 100%
75 | As Constructed Survey Data to Council Requirements. | 2 | 3108 | 4 | 5920 | 0% | 0% | 0% | 0% | 0% | 0%
76 | Geotechnical Testing by NATA Registered laboratory - Subgrade Compaction testing as specified | 1 | 5,85 | 90 | 846.6667 | 0% | 100% | 100% | 100% | 100% | 100%
77 | Sub-Base Compaction testing as specified - assume 2 layers | 2 | 92 | 88 | 846.6667 | 0% | 100% | 100% | 100% | 100% | 100%
78 | Base Compaction testing as specified | 1 | 87,85 | 95 | 423.3333 | 0% | 0% | 0% | 100% | 100% | 100%
79 | Sub-Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results - assume 2 layers | 2 | 5 | 90 | 1290 | 0% | 100% | 100% | 100% | 100% | 100%
80 | Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results | 1 | 5 | 88 | 1290 | 0% | 100% | 100% | 100% | 100% | 100%
81 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 2 | 74 | 82 | 5321.3964 | 0% | 100% | 100% | 100% | 100% | 100%
82 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 2 | 81 | 83 | 4967.1131 | 0% | 100% | 100% | 100% | 100% | 100%
83 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 1 | 82 | 84,99 | 3143.5 | 0% | 100% | 0% | 0% | 0% | 0%
84 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 83,99,110,109 | 85 | 1843.905 | 0% | 100% | 100% | 100% | 100% | 100%
85 | Prepare Dysart Bypass Rd - Middlemount Rd Intersection Subgrade Surface for Gravel Pavement & for Council / MRD Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 84 | 111,76,90,78 | 1680.0023 | 0% | 100% | 100% | 100% | 100% | 100%
86 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 91 | 87 | 925.4336 | 0% | 0% | 100% | 100% | 100% | 100%
87 | Prepare Base Gravel Surface for Primerseal & for Council / MRD Inspection, incl provision of compaction test results - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 86 | 78 | 878.8442 | 0% | 0% | 100% | 100% | 100% | 100%
88 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 1 | 98,77,80 | 91 | 7478.2426 | 0% | 100% | 100% | 100% | 100% | 100%
89 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 93 | 92 | 11116.7155 | 0% | 100% | 100% | 100% | 100% | 100%
90 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (a) Dysart Bypass Rd - Middlemount Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 85,76,79 | 93 | 9160.1584 | 0% | 100% | 100% | 100% | 100% | 100%
91 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 1 | 88 | 86,94 | 7050.9145 | 0% | 100% | 100% | 100% | 100% | 100%
92 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 89 | 98,77 | 10285.5592 | 0% | 100% | 100% | 100% | 100% | 100%
93 | Gravel Pavement In Place complete, including supply, spreading, watering, rolling and trimming:- (B) Dysart Bypass Rd - Middlemount Rd Intersection RHS -Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 90 | 89 | 8447.7016 | 0% | 100% | 100% | 100% | 100% | 100%
94 | Provisional Item Pavement Repairs - Cement Stabilise 4% by weight 200mm deep any failed areas identified by the Superintendent as ordered. | 2 | 91 | 100,95 | 5610.0655 | 0% | 0% | 0% | 0% | 0% | 0%
95 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection LHS | 1 | 78,94 | 96FF | 2355.43 | 0% | 0% | 100% | 100% | 100% | 100%
96 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Middlemount Rd Intersection RHS | 1 | 95FF | 97 | 2236.85 | 0% | 0% | 100% | 100% | 100% | 100%
97 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Middlemount Rd Intersection Complete (overlaying existing seal area) | 2 | 96 | 106 | 115460.5466 | 0% | 0% | 0% | 0% | 100% | 100%
98 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 1 | 92 | 88102 | 5701.1957 | 0% | 0% | 0% | 0% | 100% | 100%
99 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 1 | 83 | 100,84,109 | 2078.1625 | 0% | 0% | 0% | 0% | 100% | 100%
100 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 3 | 94,99 | 101 | 3600 | 0% | 0% | 100% | 100% | 100% | 100%
101 | Electrical Mains Cable Pit (Provisional Item) | 1 | 111100102 | 103 | 2452.8 | 0% | 0% | 0% | 0% | 100% | 100%
102 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 1 | 98 | 103101 | 2690.8 | 0% | 0% | 0% | 0% | 100% | 100%
103 | Soil Management Measures inclusive of: Prepare batters and drains for hydromulch placement | 1 | 102101 | 104 | 767.25 | 0% | 0% | 0% | 0% | 100% | 100%
104 | Soil Management Measures inclusive of: Hydromulch to all disturbed areas as directed (batters and drains) | 1 | 103 | 105 | 1125 | 0% | 0% | 0% | 0% | 0% | 0%
105 | Soil Management Measures inclusive of: Rock check dams as directed | 1 | 104 | 4 | 1626.4 | 0% | 0% | 0% | 0% | 0% | 0%
106 | Supply and Install New Guide Posts | 1 | 97 | 107 | 550 | 0% | 0% | 0% | 100% | 100% | 100%
107 | Supply and Install New Give Way Sign R1-2 | 1 | 106 | 108 | 338.8 | 0% | 0% | 0% | 100% | 100% | 100%
108 | Linemarking Complete,Dysart Bypass Rd - Middlemount Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 1 | 107 | 4,75 | 7500 | 0% | 0% | 0% | 0% | 0% | 100%
109 | Drainage - Ch 140 Middlemount Road Culvert 1A - Extend existing 600 x 300 RCBC RHS, complete in place incl. excavate, sand, supply, lay and backfill | 1 | 99 | 110,84 | 4014.9044 | 0% | 100% | 100% | 100% | 100% | 100%
110 | Drainage - Ch 140 Middlemount Road - 1/600 x 300 Cast Insitu Endwall and Apron to Main Roads Std Dwgs complete in place | 1 | 109 | 84 | 947.8 | 0% | 100% | 100% | 100% | 100% | 100%
111 | Provision for Traffic and Safety including an approved Traffic Management Plan required by Council prior to commencement of site works. | 13 | 85 | 112101 | 28325.0469 | 0% | 0% | 0% | 0% | 0% | 0%
112 | Construction Setout by Contractor | 2 | 111113 | 114 | 5180 | 0% | 0% | 0% | 0% | 0% | 0%
113 | Provision of evidence of Public Liability Insurance ($10 million), and Workers Compensation Insurance for the works. | 1 | 3 | 112 | 2800 | 0% | 0% | 0% | 0% | 0% | 0%
114 | Locate Existing Services (Dial-Before-You-Dig, CapVac Truck etc) as required in existing road reserves | 1 | 112 | 121 | 3200 | 0% | 0% | 0% | 0% | 0% | 0%
115 | As Constructed Survey Data to Council Requirements. | 4 | 148 | 4 | 5920 | 0% | 0% | 0% | 0% | 0% | 0%
116 | Geotechnical Testing by NATA Registered laboratory - Subgrade Compaction testing as specified | 1 | 125 | 130 | 846.6667 | 0% | 0% | 0% | 0% | 0% | 0%
117 | Sub-Base Compaction testing as specified - assume 2 layers | 2 | 132 | 128 | 846.6667 | 0% | 0% | 0% | 0% | 0% | 0%
118 | Base Compaction testing as specified | 1 | 131 | 135 | 423.3333 | 0% | 0% | 0% | 0% | 0% | 0%
119 | Sub-Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results - assume 2 layers | 3 | 5 | 130 | 1290 | 0% | 0% | 0% | 0% | 0% | 0%
120 | Base Quality Testing as specified; Full Atterbergs plus grading plus full Quarry Stockpile results | 1 | 5 | 128 | 1290 | 0% | 0% | 0% | 0% | 0% | 0%
121 | Clearing & Grubbing, removal of existing kerb and complete offsite disposal of Spoil inclusive of Dump Fees as required. | 3 | 114 | 122 | 5321.3964 | 0% | 0% | 0% | 0% | 0% | 0%
122 | Earthworks - excavate and place as embankment as directed - Cut to Spoil - to achieve boxed out deep to 500mm - material will be spoiled at IRC Tip. | 1 | 121 | 123 | 4967.1 | 0% | 0% | 0% | 0% | 0% | 0%
123 | Remove isolated soft spots in subgrade as ordered and replace with Selected Spoil material - Provisional Item | 1 | 122 | 139 | 3143.5 | 0% | 0% | 0% | 0% | 0% | 0%
124 | Prepare Dysart Bypass Rd - Golden Mile Rd Intersection Subgrade Surface for Gravel Pavement & for Council Inspection, (incl. provision of subgrade levels and compaction test results by Contractor) - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | 1 | 139 | 125 | 1270.2457 | 0% | 0% | 0% | 0% | 0% | 0%
125 | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | 1 | 124 | 116 | 2429.2717 | 0% | 0% | 0% | 0% | 0% | 0%
126 | Prepare Base Gravel Surface for Primerseal & for Council Inspection, incl provision of compaction test results - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | 1 | 131 | 127 | 599.3082 | 0% | 0% | 0% | 0% | 0% | 0%
127 | Dysart Bypass Rd - Golden Mile Rd Intersection RHS | 1 | 126 | 134 | 1264.2651 | 0% | 0% | 0% | 0% | 0% | 0%
128 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Base QT Type 2.1 @ 150mm deep | 1 | 138117120 | 131 | 4914.2737 | 0% | 0% | 0% | 0% | 0% | 0%
129 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 133 | 132 | 7480.4067 | 0% | 0% | 0% | 0% | 0% | 0%
130 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection LHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 116119 | 133 | 6310.3313 | 0% | 0% | 0% | 0% | 0% | 0%
131 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Base QT Type 2.1 @ 150mm deep | 1 | 128 | 118126 | 10149.0436 | 0% | 0% | 0% | 0% | 0% | 0%
132 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Upper Sub-Base QT Type 2.3 @ 200mm deep | 1 | 129 | 138117 | 14856.9188 | 0% | 0% | 0% | 0% | 0% | 0%
133 | Gravel Pavement - In Place complete, including supply, spreading, watering, rolling and trimming:- Dysart Bypass Rd - Golden Mile Rd Intersection RHS - Lower Sub-Base QT Type 2.5 @ 150mm deep | 1 | 130 | 129 | 12111.765 | 0% | 0% | 0% | 0% | 0% | 0%
134 | Provisional Item Pavement Repairs - Cement Stabilise 4% by weight 200mm deep any failed areas identified by the Superintendent as ordered. | 2 | 127 | 135 | 5610.0655 | 0% | 0% | 0% | 0% | 0% | 0%
135 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Golden Mile Rd Intersection LHS | 1 | 118134 | 136FF | 1525.37 | 0% | 0% | 0% | 0% | 0% | 0%
136 | Bitumen Seal - complete in place (10mm primerseal ) ; spray rates nominally to be 1.1 l/sqm C170 - SEAL DESIGN TO BE CONFIRMED - Dysart Bypass Rd - Golden Mile Rd Intersection RHS | 1 | 135FF | 137 | 3217.83 | 0% | 0% | 0% | 0% | 0% | 0%
137 | Asphaltic Concrete Pavement MRD Type DG14 and 60 mm minimum thickness - complete in place. - Dysart Bypass Rd - Golden Mile Rd Intersection Complete (overlaying existing seal area) | 2 | 136 | 146 | 121115.2984 | 0% | 0% | 0% | 0% | 0% | 0%
138 | Medians Kerb at Intersections - Type 5 Concrete Kerb in minimum 25 MPa concrete | 4 | 132 | 128142 | 5701.1988 | 0% | 0% | 0% | 0% | 0% | 0%
139 | Street Lighting - Conduits and Bases - Electrical Mains Trenching and Conduiting including bends, draw-wire, sand, bed, backfill, warning tape: 1 x 100 dia LV (HD) + HARD COVER (Provisional Item) | 1 | 123 | 140124 | 2770.989 | 0% | 0% | 0% | 0% | 0% | 0%
140 | Electrical Under Road Bore complete including conduit bends and draw-wire: 1 x 100 dia LV (HD) (Provisional Item) | 3 | 139 | 142 | 3860 | 0% | 0% | 0% | 0% | 0% | 0%
141 | Electrical Mains Cable Pit (Provisional Item) | 4 | 142 | 143 | 2452.8 | 0% | 0% | 0% | 0% | 0% | 0%
142 | Street Light Bases Complete in Place, including supply of rag bolts and excluding Conduiting Major Pole Base (NB - ALL 10.5m POLES NEED THE LARGER BASES) | 1 | 138140 | 141 | 2690.8 | 0% | 0% | 0% | 0% | 0% | 0%
143 | Soil Management Measures inclusive of: - Prepare batters and drains for hydromulch placement | 4 | 141 | 144 | 767.25 | 0% | 0% | 0% | 0% | 0% | 0%
144 | Hydromulch to all disturbed areas as directed (batters & drains) | 1 | 143 | 145 | 1125 | 0% | 0% | 0% | 0% | 0% | 0%
145 | Rock check dams as directed | 1 | 144 | 4,18 | 1626.4 | 0% | 0% | 0% | 0% | 0% | 0%
146 | Supply and Install New Guide Posts | 4 | 137 | 147 | 500 | 0% | 0% | 0% | 0% | 0% | 0%
147 | Supply and Install New Give Way Sign R1-2 | 1 | 146 | 148 | 338.8 | 0% | 0% | 0% | 0% | 0% | 0%
148 | Linemarking Complete,Dysart Bypass Rd - Golden Mile Rd Intersection - Reinstate existing and new lines as per drawing No 842 - R19 | 1 | 147 | 115 | 7500 | 0% | 0% | 0% | 0% | 0% | 0%
161 | Remove & replace unsuitable - ch0 | 1 | 19 | 20 | 3300.675 | 0% | 100% | 100% | 100% | 100% | 100%
162 | Addiitonal drainage items | 4 | 18 | 19 | 7048.884 | 0% | 100% | 100% | 100% | 100% | 100%
168 | Stabilisation of Edges - Bypass Road | 5 | 24 | 23 | 22336.2232 | 0% | 0% | 0% | 0% | 0% | 100%